## Slide 1: The 5 Stages of Downscoping Or: How We Learned to Stop Worrying and Love the Cut
Team CIGAM

## Slide 2: Vision
From the HLDD: “The core idea of this game is a system that a player can never fully explore. We want them to feel like there’s always a new idea to come up with.”
A procedurally parsed magic system that a player could learn about
A world that a player could meaningfully interact with

## Slide 3: Demo

## Slide 4: The 5 Stages of Downscoping
Denial
Anger
Bargaining
Depression
Acceptance

## Slide 5: Denial: Refusing to Accept Failures of Scope
Insistence that could do more than we could
Overestimation of availability and underestimation of difficulty

## Slide 6: Lessons Learned
Overestimate how long overall tasks will take
    While large tasks may take the time expected, unexpected small tasks add up
Don’t hand-wave art/sound/UI/frontend (we’ll find someone!)
    If it has to be done, it takes time
Giving meaningful player feedback is difficult
    It takes blood, sweat, tears, time, and tears. And sweat.

## Slide 7: Anger: Why Isn’t the Game Done!?
Managing communications and “Storming”
Things take longer than expected; things immediately feel behind
Learning new libraries takes time

## Slide 8: Lessons Learned
Ask for help early and often; Volunteer help early and often
    Initial timidity causes unnecessary technical delay
Code in groups, especially early on
    20% time in group coding, 50% final code produced in group

## Slide 9: Bargaining: If We Cut the Stretch Goals, That’s Enough
We did cut down to working size, but it should have been sooner
“The backend works” as excuse for nonexistent frontend
    Ok to a degree, but inhibits early testing

## Slide 10: Lessons Learned
Cut things earlier, especially if in the back of everyone’s mind
Attempt early vertical slices
    Notice earlier when frontend aspects will burn through time

## Slide 14: Depression: Are we even going to have a game?
Realizing too late how big of a hole you’ve dug yourself
Dealing with crunch
Batches of time in non-interesting tasks
    Morale falters

## Slide 15
C-C-C-COMBO BREAKER

## Slide 16: Lessons Learned
Refocus based on HLDD if needed
    Remind yourself why you were excited about the project in the first place
Crunching in groups avoids miscommunication delays
    And you keep each other on track

## Slide 17: Acceptance: Proof of Concept
Cut down to the core design, make that work
A working game now is better than a perfect game tomorrow
    It may not be ideal, but functional kludge is better than unfinished elegance
Be excited about what the game actually offers, even if it wasn’t what was originally intended!
    I still submit that I learned more from Frog Fractions than Number Munchers.

## Slide 22: Lessons Learned
“Serenity to accept the things I cannot change, The courage to change the things I can, And the wisdom to know the difference”
Cutting down to a decent skeleton that holds true to the initial vision
    The initial vision may be out of scope, but you can at least have a proof of concept!

## Slide 23: This is the last slide
Cause I couldn’t think of how to end it.
Shiet.